## Sheet1
Task | Task Breakdown | Plan Effort (Person-Days) | Actual Effort (Person-Days) | Complete
1 | User Registration/Login/Auth System | 5 | 7 | Yes
2 | Profile Management | 4 | 6 | Yes
3 | Resume Upload & Storage | 6 | 9 | Yes
4 | Job Browse/Search/Filter & Application System | 8 | 11 | Yes
5 | AI Recommendation Engine | 5 | 8 | Yes
6 | Interview Scheduling System | 4 | 6 | Yes
7 | Registration/Login/Profile Forms & Pages | 7 | 10 | Yes
8 | Job Search & Listing Pages | 6 | 8 | Yes
9 | Resume Upload & Management Interface | 5 | 7 | Yes
10 | Dashboard | 7 | 10 | Yes
11 | Employer Registration/Login/Auth | 3 | 4 | Yes
12 | Job/Internship Posting Management (CRUD) | 5 | 7 | Yes
13 | Candidate Profile & Resume Viewing | 4 | 6 | Yes
14 | Interview Scheduling & Feedback System | 5 | 7 | Yes
15 | Integration with shared Messaging module | 3 | 5 | Yes
16 | Dashboard for posting jobs and viewing applicants | 8 | 11 | Yes
17 | Candidate Review & Profile Interface | 5 | 7 | Yes
18 | Interview Management UI | 5 | 7 | Yes
19 | Admin Auth & Privileges | 2 | 3 | No
20 | User Account Management (Activate/Suspend/Delete) | 4 | 6 | No
21 | Job Post Monitoring & Takedown | 3 | 5 | No
22 | Basic Analytics Data Aggregation | 3 | 5 | No
23 | Admin Dashboard with overview and controls | 6 | 8 | No
24 | User Management & Report Views | 4 | 6 | No
25 | Real-time Messaging System (WebSockets) | 10 | 15 | No
26 | Database Schema Design & Setup | 5 | 7 | No
27 | Shared UI Components (Header, Nav, etc.) | 3 | 5 | No
28 | Messaging Interface Component | 2 | 4 | No
29 | Testing (Unit, Integration, E2E) | 10 | 15 | No
30 | Deployment Setup & CI/CD Pipeline | 5 | 8 | No
31 | Project Management & Communication | 5 | 8 | No